Process Sheet: Autonomous Vehicle Software Simulation Project

- Requirement Engineering

| Steps | PDCA Phase | Input | Tools / Methods Used | Critical Parameters | Output / Check |
| --- | --- | --- | --- | --- | --- |
| 1 | PLAN – Identify Objective | Challenge V2 Docs, Project List | Requirement Decomposition, Simulator Profiling | Target Speed 50 MPH, GPU VRAM > 4 GB | Architectural Roadmap |
| 2 | PLAN – Analyze Root Data | Camera, Lidar, Radar Streams | Histogram Analysis, SNR Check | Resolution, Noise Profiles | Preprocessing Strategy |
| 3 | DO – Implement Environment | Unity Simulator | Conda Setup, Lane Finding (Prj 1) | Library Compatibility | Operational Simulator |
| 4 | CHECK – Evaluate Feasibility | Test Loop | FPS & Memory Monitoring | FPS > 30, Memory < 80% | Validated Connectivity |
| 5 | ACT – Standardize Workflow | Verified Environment | Git, Docker | Reproducib-ility | Standard Dev Setup |
| 6 | ACT – Rollout & Monitor | Dev Environment | CI Pipeline | System Uptime | DL-Ready Platform |

- Concept Design – Deep Learning Perception

| Steps | PDCA Phase | Input | Tools / Methods Used | Critical Parameters | Output / Check |
| --- | --- | --- | --- | --- | --- |
| 1 | PLAN – Architecture | Traffic Sign Data, Steering Logs | CNN Search (LeNet, VGG, PilotNet) | Params, Train/Val Split | DL Architecture |
| 2 | PLAN – Data Preparation | Imbalanced Dataset | Augmentation (Flip, Brightness) | Class Balance | Robust Dataset |
| 3 | DO – Model Training | Preprocessed Data | TF / Keras (Prj 2, 3) | Loss, LR, Epochs | Trained Models |
| 4 | CHECK – Performance | Validation Set | Confusion Matrix, MSE | Accuracy > 93% | Validated Models |
| 5 | ACT – Improve | Overfitting | Dropout, L2, Early Stop | Generalization | Robust Network |
| 6 | ACT – Deploy | Optimized Models | Model Freezing | Latency < 20 ms | Deployed Perception |

- Embodiment Design – Advanced Vision Stack

| Steps | PDCA Phase | Input | Tools / Methods Used | Critical Parameters | Output / Check |
| --- | --- | --- | --- | --- | --- |
| 1 | PLAN – Noise Analysis | Shadows, Glare, Curves | HLS / LAB Analysis | Thresholds | Vision Logic |
| 2 | PLAN – Detection Methods | Video Stream | HOG, CNN Comparison | Cost vs Accuracy | Method Selection |
| 3 | DO – Implementation | Raw Frames | Warping, YOLO, FCN | Perspective Matrix | Perception Module |
| 4 | CHECK – Reliability | Test Clips | IoU, Visual Debug | FP < 2% | Reliable Tracking |
| 5 | ACT – Improve | Jitter | Temporal Smoothing | Stability | Stable Output |
| 6 | ACT – Integration | Stable Pipeline | Main Loop Hook | FPS > 25 | Integrated Vision |

- Detail Design – Sensor Fusion & State Estimation

| Steps | PDCA Phase | Input | Tools / Methods Used | Critical Parameters | Output / Check |
| --- | --- | --- | --- | --- | --- |
| 1 | PLAN – Modeling | Noisy Sensor Data | CTRV, Gaussian Theory | State Vector | Motion Model |
| 2 | PLAN – Covariance Analysis | Sensor Specs | Jacobians, Hessians | Q / R Matrices | Measurement Model |
| 3 | DO – Filters | Sensor Measurements | EKF, UKF, Particle Filter | Sigma Points | Fusion Module |
| 4 | CHECK – Accuracy | Ground Truth | RMSE, NIS | RMSE < 0.10 | Precise Localization |
| 5 | ACT – Improve | Divergence | Noise Tuning | Consistency | Optimized Filters |
| 6 | ACT – Deployment | Tuned Filters | C++ Optimization | < 3 ms Cycle | Real-Time State |

- Trajectory Planning & Strategy

| Steps | PDCA Phase | Input | Tools / Methods Used | Critical Parameters | Output / Check |
| --- | --- | --- | --- | --- | --- |
| 1 | PLAN – Route Logic | Highway Map | FSM, Frenet | Speed 50 MPH | Behavior Planner |
| 2 | PLAN Cost Design | Traffic Data | Collision / Lane Costs | Weights | Cost Function |
| 3 | DO – Trajectory | Waypoints | Splines | Jerk Minimization | Smooth Path |
| 4 | CHECK – Safety | Dense Traffic | Collision Checking | Accel/Jerk Limits | Safe Path |
| 5 | ACT – Improve | Stuck States | Horizon Tuning | Comfort | Refined Planner |
| 6 | ACT – Integration | Final Logic | Fusion Output | Planning Rate | Nav Module |

- Control System Development

| Steps | PDCA Phase | Input | Tools / Methods Used | Critical Parameters | Output / Check |
| --- | --- | --- | --- | --- | --- |
| 1 | PLAN – Vehicle Model | Physics Params | Kinematic/Dynamic | CTE, Heading Error | Control Specs |
| 2 | PLAN – Actuation | Latency Model | Limit Analysis | Steering ±25° | Compensation |
| 3 | DO – Controllers | Planned Path | PID, MPC | Kp Ki Kd | Control Commands |
| 4 | CHECK – Stability | Curves | Feedback Analysis | Oscillation | Stable Control |
| 5 | ACT – Improve | Instability | Twiddle / Manual | Smoothness | Optimized Control |
| 6 | ACT – Integration | Validated Control | System Bridge | Latency < 100 ms | Full Control |

- Simulation Testing & Final Validation

| Steps | PDCA Phase | Input | Tools / Methods Used | Critical Parameters | Output / Check |
| --- | --- | --- | --- | --- | --- |
| 1 | PLAN – Test Design | 6946 m Highway | Edge Cases | Zero Collisions | Test Plan |
| 2 | PLAN – Resources | Full Stack | CPU/GPU Balance | Threads | Optimization |
| 3 | DO – Full Run | Integrated System | End-to-End Sim | Telemetry | Autonomous Lap |
| 4 | CHECK – Review | Logs | Safety Automation | Lap < 5 min | Challenge Pass |
| 5 | ACT – Improve | Minor Issues | Refactoring | Readability | Polished Code |
| 6 | ACT – Finalize | Final Build | Docs & Report | Clarity | Submission |

LIST OF ACTIVITIES

Requirement Engineering

- Decompose Requirements: Analyze Challenge V2 specifications into 13 distinct modules.

- Audit Hardware: Profile GPU VRAM/CPU threads for deep learning loads.

- Provision Environment: Install Unity Simulator (SAEISS build) and verifying compatibility.

- Configure Stack: Setup Anaconda envs, TensorFlow/Keras, and C++ toolchains.

- Define Thresholds: Set strict limits for RMSE (<0.10), Max Jerk (<10m/s³), Latency (<100ms).

- Initialize Pipeline: Script raw telemetry ingestion (Camera, Lidar, Radar).

Concept Design

- Architect CNN: Design convolutional layers for Traffic Sign Classification.

- Preprocess Data: Normalize/Augment image datasets (jitter, rotation) for balance.

- Train Classifier (Prj 2): Execute supervised learning to achieve >93% accuracy.

- Design Network: Architect NVIDIA PilotNet for end-to-end Behavioral Cloning.

- Log Telemetry: Record manual driving laps for Steering/Image dataset generation.

- Train Model (Prj 3): Minimize Mean Squared Error (MSE) on steering predictions.

Embodiment Design

- Calibrate Optics: Compute camera matrix/distortion coefficients via chessboard images.

- Warp Perspective: Implement Bird's-Eye-View transformation for curvature analysis.

- Isolate Lanes: Apply HLS color thresholding and Sobel gradient filters (Prj 4).

- Track Lanes: Implement Sliding Window Search for line detection.

- Extract Features: Compute Histogram of Oriented Gradients (HOG) for object recognition.

- Train Detector (Prj 5): Train Linear SVM/YOLO to identify vehicles/obstacles

Detail Design

- Derive Models: Formulate Constant Turn Rate and Velocity (CTRV) physics.

- Linearize Measurement: Calculate Jacobian Matrices for Extended Kalman Filter.

- Fuse Sensors (Prj 6): Code C++ EKF algorithm for Lidar/Radar data fusion.

- Generate Sigma Points: Implement Augmentation for Unscented Kalman Filter (UKF).

- Tune Covariance: Optimize Process Noise (Q) parameters for UKF (Prj 7).

- Localize Vehicle (Prj 8): Implement Particle Filter (MCL) for "Kidnapped" recovery.

Sourcing (Logic & Maps)

- Parse Map: Ingest sparse highway waypoints (x, y, s, d) from simulator.

- Transform Coordinates: Develop Cartesian-to-Frenet conversion logic.

- Design FSM: Define finite states (Keep Lane, Change Left/Right) for planner.

- Define Costs: Assign penalty weights for collision, buffer, and efficiency.

- Integrate Traffic Lights (Prj 13): Link classifier output to decision planner logic.

- Interpolate Path: Generate jerk-minimized trajectories using C++ splines.

Prototype Building

- Model Dynamics: Analyze simulator actuator limits (-25° steering, throttle).

- Code PID (Prj 9): Implement Proportional-Integral-Derivative error correction.

- Tune Gains: Iteratively adjust Kp, Ki, Kd to damp oscillation.

- Set Constraints: Define boundaries for latency (100ms) and physics.

- Solve MPC (Prj 10): Integrate Ipopt/CppAD libraries for optimization.

- Close Loop: Bridge Path Planner output to Control System input.

Prototype Testing

- Validate Localization: Measure position error in "Kidnapped" scenario.

- Verify Fusion: Check RMSE values against target (0.10) in tracker scene.

- Run Highway Loop: Launch integrated stack on 6946m simulator track.

- Log Telemetry: Monitor real-time speed, accel, and jerk data.

- Audit Safety: Verify collision-free performance during lane changes.

- Check Compliance: Confirm adherence to 50 MPH limit and lane logic.

Iteration for Optimization

- Analyze Divergence: Identify RMSE spikes and re-tune noise covariances.

- Refine Vision: Adjust thresholding to handle shadow/glare edge cases.

- Tune Horizon: Modify MPC time steps (N, dt) for smoother actuation.

- Optimize Code: Refactor C++ loops to boost system FPS/reduce latency.

- Adjust FSM: Tune cost weights to prevent "stuck" states behind traffic.

- Stress Test: Execute continuous multi-lap run for stability verification.

Documenting for Sharing

- Draft Architecture: Diagram system data flow between modules.

- Plot Performance: Visualize RMSE, CTE, and Speed logs for report.

- Refactor Base: Standardize variable naming and remove debug prints.

- Write README: Document installation dependencies and run instructions.

- Record Demo: Capture video clips/GIFs of successful challenge completion.

- Package Delivery: Archive source code and Technical Report for submission.

DURATION TABLE
REQUIREMENT ENGINEERING

| ID | Activity Name | Duration (Hrs) |
| --- | --- | --- |
| 1 | Decompose Requirements | 2.0 |
| 2 | Audit Hardware (GPU/CPU) | 1.0 |
| 3 | Provision Environment (Unity/SAEISS) | 3.0 |
| 4 | Configure Stack (Conda/C++) | 4.0 |
| 5 | Define Thresholds (RMSE, Jerk) | 2.0 |
| 6 | Initialize Data Pipeline | 2.0 |
|  | Total | 14.0 |

CONCEPT DESIGN

| ID | Activity Name | Duration (Hrs) |
| --- | --- | --- |
| 1 | Architect CNN (Traffic Signs) | 3.0 |
| 2 | Preprocess Data (Augmentation) | 5.0 |
| 3 | Train Classifier (Prj 2) | 6.0 |
| 4 | Design Network (PilotNet) | 3.0 |
| 5 | Log Telemetry (Simulator Laps) | 4.0 |
| 6 | Train Model (Prj 3 - Cloning) | 7.0 |
|  | Total | 28.0 |

EMBODIMENT DESIGN

| ID | Activity Name | Duration (Hrs) |
| --- | --- | --- |
| 1 | Calibrate Optics (Camera Matrix) | 2.0 |
| 2 | Warp Perspective (Bird's Eye) | 3.0 |
| 3 | Isolate Lanes (HLS/Sobel) | 6.0 |
| 4 | Track Lanes (Sliding Window) | 4.0 |
| 5 | Extract Features (HOG) | 3.0 |
| 6 | Train Detector (Prj 5 - SVM) | 6.0 |
|  | Total | 24.0 |

DETAIL DESIGN

| ID | Activity Name | Duration (Hrs) |
| --- | --- | --- |
| 1 | Derive Models (CTRV Physics) | 3.0 |
| 2 | Linearize Measurement (Jacobian) | 4.0 |
| 3 | Fuse Sensors (Prj 6 - EKF) | 7.0 |
| 4 | Generate Sigma Points (UKF) | 3.0 |
| 5 | Tune Covariance (Prj 7) | 6.0 |
| 6 | Localize Vehicle (Prj 8 - MCL) | 5.0 |
|  | Total | 28.0 |

SOURCING (LOGIC & MAPS)

| ID | Activity Name | Duration (Hrs) |
| --- | --- | --- |
| 1 | Parse Map (Waypoints) | 2.0 |
| 2 | Transform Coordinates (Frenet) | 3.0 |
| 3 | Design FSM (Lane Logic) | 5.0 |
| 4 | Define Costs (Penalty Weights) | 2.0 |
| 5 | Integrate Traffic Lights (Prj 13) | 4.0 |
| 6 | Interpolate Path (Splines) | 5.0 |
|  | Total | 21.0 |

PROTOTYPE BUILDING

| ID | Activity Name | Duration (Hrs) |
| --- | --- | --- |
| 1 | Model Dynamics (Actuators) | 2.0 |
| 2 | Code PID (Prj 9) | 3.0 |
| 3 | Tune Gains (Kp, Ki, Kd) | 5.0 |
| 4 | Set Constraints (Latency) | 2.0 |
| 5 | Solve MPC (Prj 10 - Optimization) | 8.0 |
| 6 | Close Loop (Plan to Control) | 2.0 |
|  | Total | 22.0 |

PROTOTYPE TESTING

| ID | Activity Name | Duration (Hrs) |
| --- | --- | --- |
| 1 | Validate Localization (Error Check) | 2.0 |
| 2 | Verify Fusion (RMSE Check) | 2.0 |
| 3 | Run Highway Loop (Full Sim) | 4.0 |
| 4 | Log Telemetry (Speed/Jerk) | 2.0 |
| 5 | Audit Safety (Collision Check) | 4.0 |
| 6 | Check Compliance (Traffic Rules) | 2.0 |
|  | Total | 16.0 |

ITERATION FOR OPTIMIZATION

| ID | Activity Name | Duration (Hrs) |
| --- | --- | --- |
| 1 | Analyze Divergence (Fix Math) | 5.0 |
| 2 | Refine Vision (Fix Shadows) | 6.0 |
| 3 | Tune Horizon (Fix Oscillation) | 4.0 |
| 4 | Optimize Code (C++ Memory) | 7.0 |
| 5 | Adjust FSM (Fix Stuck States) | 6.0 |
| 6 | Stress Test (Multi-Lap) | 4.0 |
|  | Total | 32.0 |

DOCUMENTATION FOR SHARING

| ID | Activity Name | Duration (Hrs) |
| --- | --- | --- |
| 1 | Draft Architecture (Diagrams) | 3.0 |
| 2 | Plot Performance (Data Viz) | 2.0 |
| 3 | Refactor Base (Clean Code) | 5.0 |
| 4 | Write README (Install Guide) | 2.0 |
| 5 | Record Demo (Video/GIF) | 2.0 |
| 6 | Package Delivery (Zip/Submit) | 1.0 |
|  | Total | 15.0 |

ACTIVITY PRECEDENCE TABLE

| ID | Activity Name | Immediate Predecessors |
| --- | --- | --- |
| 1 | Decompose Requirements | -- (Start) |
| 2 | Audit Hardware (GPU/CPU) | 1 |
| 3 | Provision Environment (Unity/SAEISS) | 2 |
| 4 | Configure Stack (Conda/C++) | 3 |
| 5 | Define Thresholds (RMSE, Jerk) | 1 |
| 6 | Initialize Data Pipeline | 4 |
| 7 | Architect CNN (Traffic Signs) | 6 |
| 8 | Preprocess Data (Augmentation) | 6 |
| 9 | Train Classifier (Prj 2) | 7, 8 |
| 10 | Design Network (PilotNet) | 6 |
| 11 | Log Telemetry (Simulator Laps) | 3 |
| 12 | Train Model (Prj 3 - Cloning) | 10, 11 |
| 13 | Calibrate Optics (Camera Matrix) | 6 |
| 14 | Warp Perspective (Bird's Eye) | 13 |
| 15 | Isolate Lanes (HLS/Sobel) | 14 |
| 16 | Track Lanes (Sliding Window) | 15 |
| 17 | Extract Features (HOG) | 6 |
| 18 | Train Detector (Prj 5 - SVM) | 17 |
| 19 | Derive Models (CTRV Physics) | 4 |
| 20 | Linearize Measurement (Jacobian) | 19 |
| 21 | Fuse Sensors (Prj 6 - EKF) | 6, 20 |
| 22 | Generate Sigma Points (UKF) | 19 |
| 23 | Tune Covariance (Prj 7) | 21, 22 |
| 24 | Localize Vehicle (Prj 8 - MCL) | 23 |
| 25 | Parse Map (Waypoints) | 6 |
| 26 | Transform Coordinates (Frenet) | 25 |
| 27 | Design FSM (Lane Logic) | 26 |
| 28 | Define Costs (Penalty Weights) | 27 |
| 29 | Integrate Traffic Lights (Prj 13) | 9, 27 |
| 30 | Interpolate Path (Splines) | 27, 28 |
| 31 | Model Dynamics (Actuators) | 4 |
| 32 | Code PID (Prj 9) | 31 |
| 33 | Tune Gains (Kp, Ki, Kd) | 32 |
| 34 | Set Constraints (Latency) | 31 |
| 35 | Solve MPC (Prj 10 - Optimization) | 34 |
| 36 | Close Loop (Plan to Control) | 30, 33, 35 |
| 37 | Validate Localization (Error Check) | 24 |
| 38 | Verify Fusion (RMSE Check) | 23 |
| 39 | Run Highway Loop (Full Sim) | 12, 16, 18, 29, 36 |
| 40 | Log Telemetry (Speed/Jerk) | 39 |
| 41 | Audit Safety (Collision Check) | 40 |
| 42 | Check Compliance (Traffic Rules) | 40 |
| 43 | Analyze Divergence (Fix Math) | 38, 41 |
| 44 | Refine Vision (Fix Shadows) | 16, 41 |
| 45 | Tune Horizon (Fix Oscillation) | 35, 41 |
| 46 | Optimize Code (C++ Memory) | 39 |
| 47 | Adjust FSM (Fix Stuck States) | 39 |
| 48 | Stress Test (Multi-Lap) | 43, 44, 45, 46, 47 |
| 49 | Draft Architecture (Diagrams) | 48 |
| 50 | Plot Performance (Data Viz) | 40, 48 |
| 51 | Refactor Base (Clean Code) | 48 |
| 52 | Write README (Install Guide) | 51 |
| 53 | Record Demo (Video/GIF) | 48 |
| 54 | Package Delivery (Zip/Submit) | 52, 53 |

CRITICAL PATH (PROJECT WIDE, 54 ACTIVITIES)

Critical Path Sequence (Longest Dependency Chain, Start → Finish)

1 → 2 → 3 → 4 → 5 → 6 → 7 → 8 → 9 → 10 → 11 → 12 → 13 → 14 → 15 → 16 → 17 → 18 → 19 → 20 → 21 → 22 → 23 → 24 → 25 → 26 → 27 → 28 → 29 → 30 → 31 → 32 → 33 → 34 → 35 → 36 → 37 → 38 → 39 → 40 → 41 → 42 → 43 → 44 → 45 → 46 → 47 → 48 → 49 → 50 → 51 → 52 → 53 → 54

1. Requirement Engineering (1–6)

1 → 2 → 3 → 4 → 5 → 6

(Decompose Reqs → Hardware Audit → Environment Setup → Config Stack → Define Thresholds → Initialize Pipeline)

2. Concept Design (7–12)

7 → 8 → 9 → 10 → 11 → 12

(CNN Architecture → Data Preprocessing → Train Classifier → PilotNet Design → Log Telemetry → Train Behavioral Model)

3. Embodiment Design (13–18)

13 → 14 → 15 → 16 → 17 → 18

(Camera Calib → Perspective Warp → Lane Isolation → Window Search → HOG Extraction → Train Vehicle Detector)

4. Detail Design (19–24)

19 → 20 → 21 → 22 → 23 → 24

(Derive Physics → Linearize Matrices → EKF Fusion → UKF Sigma Points → Tune Covariances → Particle Filter Loc)

5. Sourcing (Logic & Maps) (25–30)

25 → 26 → 27 → 28 → 29 → 30

(Parse Map → Frenet Transform → FSM Logic → Define Costs → Integrate Signals → Spline Interpolation)

6. Prototype Building (31–36)

31 → 32 → 33 → 34 → 35 → 36

(Model Dynamics → Code PID → Tune Gains → MPC Constraints → Solve Optimization → Close Control Loop)

7. Prototype Testing (37–42)

37 → 38 → 39 → 40 → 41 → 42

(Validate Loc → Verify Fusion → Run Highway Loop → Log Telemetry → Audit Safety → Check Rules)

8. Iteration / Optimization (43–48)

43 → 44 → 45 → 46 → 47 → 48

(Analyze Errors → Refine Vision → Tune Horizon → Optimize Code → Adjust Logic → Final Stress Test)

9. Documenting & Closure (49–54)

49 → 50 → 51 → 52 → 53 → 54

(Draft Diagrams → Plot Performance → Clean Code → Write README → Record Demo → Final Submission)

PARALLEL AND SERIES PATH

START

↓

(Phase 1: Setup)

Backbone: 1 → 2 → 3 → 4 → 5 → 6

↓

↓ (Split for Phase 2 & 3)

↓

(Phase 2 & 3: Vision)

Backbone: 10 → 11 → 12 → 13 → 14 → 15 → 16

↘

(Parallel Branch A) 7 → 8 → 9 (Traffic Signs)

↘

(Parallel Branch B) 17 → 18 (Vehicle Detection)

↓

↓ (Merge & Split for Phase 4)

↓

(Phase 4: Fusion)

Backbone: 19 → 20 → 21 → 24

↘

(Parallel Branch C) 22 → 23 (UKF Logic)

↓

↓

(Phase 5: Planning)

Backbone: 25 → 26 → 27 → 28 → 30

↘

(Parallel Branch D) 29 (Traffic Light Integration)

↓

↓ (Merge & Split for Phase 6)

↓

(Phase 6: Control)

Backbone: 31 → 32 → 33 → 36

↘

(Parallel Branch E) 34 → 35 (MPC Optimization)

↓

↓

(Phase 7, 8, 9: Linear Finish)

Backbone: 37 → 38 → 39 → 40 → 41 → 42 → 43 ... → 54

↓

END

OVERALL PARALLEL AND SERIES PATH

| Phase | Parallel Path Nodes | Series (Main) Path Nodes |
| --- | --- | --- |
| Requirement Engineering | — (All steps are foundational) | 1 → 2 → 3 → 4 → 5 → 6 |
| Concept Design | 7 → 8 → 9 (Traffic Sign Development — runs in parallel with main path) | 10 → 11 → 12 (Behavioral Cloning) |
| Embodiment Design | 17 → 18 (Object Detection — runs in parallel with main path) | 13 → 14 → 15 → 16 (Advanced Lane Finding) |
| Detail Design | 22 (UKF Sigma Point Generation — parallel to EKF Jacobian) | 19 → 20 → 21 → 23 → 24 |
| Sourcing (Logic) | 29 (Traffic Light Integration) | 25 → 26 → 27 → 28 → 30 |
| Prototype Building | 31 → 34 → 35 (Model Predictive Control — parallel to PID) | 32 → 33 → 36 (PID Controller) |
| Prototype Testing | 37 → 38 (Unit Testing) | 39 → 40 → 41 → 42 (Full System Closed Loop) |
| Iteration / Optimization | 44 → 46 (Vision & Code Optimization) | 43 → 45 → 47 → 48 |
| Documentation / Closure | 49 ↔ 50 (Overlapping activities) | 51 → 52 → 53 → 54 |

Phase 1: Setup (The Linear Start)

1 -> 2

2 -> 3

3 -> 4

4 -> 5

5 -> 6

The Big Split (Parallel Engineering starts here)

Note: Step 6 triggers multiple streams.

6 -> 7   (Starts Deep Learning Stream)

6 -> 10  (Starts Behavioral Stream)

6 -> 13  (Starts Vision Stream)

6 -> 17  (Starts Detection Stream)

6 -> 19  (Starts Fusion/Math Stream)

6 -> 25  (Starts Planning Stream)

6 -> 31  (Starts Control Stream)

Stream 1: Deep Learning (Traffic Signs)

7 -> 8

8 -> 9

9 -> 29  (Output needed for Traffic Light Logic)

Stream 2: Behavioral Cloning

10 -> 11

11 -> 12

12 -> 39 (Output needed for Final Sim)

Stream 3: Computer Vision (Lanes)

13 -> 14

14 -> 15

15 -> 16

16 -> 39 (Output needed for Final Sim)

Stream 4: Object Detection

17 -> 18

18 -> 39 (Output needed for Final Sim)

Stream 5: Sensor Fusion (The Math)

19 -> 20

20 -> 21

21 -> 23

19 -> 22

22 -> 23

23 -> 24

24 -> 37 (Output needed for Testing)

Stream 6: Sourcing Logic (Planning)

25 -> 26

26 -> 27

27 -> 28

27 -> 29

28 -> 30

29 -> 30

30 -> 36 (Output needed for Control Loop)

Stream 7: Prototype Building (Controls)

31 -> 32

32 -> 33

31 -> 34

34 -> 35

33 -> 36

35 -> 36

Phase 7: Testing (The Big Integration Merge)

36 -> 39

24 -> 37

37 -> 38

38 -> 43

39 -> 40

40 -> 41

40 -> 42

41 -> 43

41 -> 44

41 -> 45

41 -> 47

Phase 8: Optimization (Feedback Loops)

43 -> 48

44 -> 48

45 -> 48

46 -> 48

47 -> 48

39 -> 46

39 -> 47

Phase 9: Documentation (The Finish)

48 -> 49

48 -> 50

48 -> 51

48 -> 53

49 -> 54

50 -> 54

51 -> 52

52 -> 54

53 -> 54

ACTIVITY

NETWORK

DIAGRAM